## 4ec63bd6e66ae6f894d8c2609ca7bc5
WBS # | Name / Title | Type | Start Date | End Date | Estimated Hours | Actual Hours | Percent Complete | Resources | Predecessors | Notes | Comments | Task Color
1 | Translation and Language Contact in Literature (TLCL) | project | 2023-09-25 | 2030-11-29 | 0 | 0 | 0
1.1 | WP1: Translation studies and original writing | group | 2023-12-01 | 2027-01-04 | 0 | 0 | 0
1.1.1 | Article on unit of translation | task | 2024-03-01 | 2024-07-31 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.1.2 | Article on translationality | task | 2024-02-01 | 2024-12-04 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.1.3 | Article on Dostoevsky | task | 2024-12-03 | 2025-12-03 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.3.1 |  |  | purple1
1.1.4 | Article on linguistic relativity and translation | task | 2023-12-01 | 2024-03-29 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | blue2
1.1.5 | Proposal for co-edited book on Pevear and Volokhonsky | task | 2024-06-03 | 2024-09-02 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | blue2
1.1.6 | Co-edited book on Pevear and Volokhonsky | task | 2025-07-01 | 2027-01-04 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.1.5 |  |  | blue2
1.2 | WP2: Language contact and cross-lingual stylistic transfer | group | 2023-09-25 | 2030-11-29 | 0 | 0 | 0
1.2.1 | Submit proposal for Multilingual Anthology | task | 2024-05-02 | 2024-11-01 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.2.2 | Edited volume on language contact in literature | task | 2026-10-06 | 2028-04-24 | 0 | 0 | 0 | Research Associates 1&2 | 1.2.5,1.2.7 |  |  | blue2
1.2.3 | Two case studies on language contact | task | 2023-09-25 | 2026-09-23 | 0 | 0 | 0 | Research Associates 1&2 |  |  |  | blue2
1.2.4 | Monograph - submit proposal | task | 2027-07-14 | 2027-11-30 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.1.1,1.1.2,1.1.3,1.3.1 |  |  | purple1
1.2.5 | Organise conference at host institution | task | 2026-02-04 | 2026-12-07 | 0 | 0 | 0 | Research Associates 1&2 |  |  |  | blue2
1.2.6 | Monograph - prepare full draft for submission | task | 2028-01-03 | 2030-11-29 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.2.4 |  |  | purple1
1.2.7 | Proposal for a Routledge series on language contact & inaugural edited volume | task | 2026-05-01 | 2026-12-04 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | blue2
1.3 | WP3: Stylometry | group | 2024-02-01 | 2030-11-01 | 0 | 0 | 0
1.3.1 | Create corpora (Dostoevsky, Nabokov, modernism) | task | 2024-10-01 | 2025-09-02 | 0 | 0 | 0 | Research Associate (DH), Eugenia Kelbert Rudan |  |  |  | blue2
1.3.2 | Develop Bukvik and LitTerra and use for research in project | task | 2024-02-01 | 2030-11-01 | 0 | 0 | 0 | Research Associate (DH) |  |  |  | blue2
1.3.3 | Integrate existing software with Bukvik and reproduce results where possible | task | 2024-03-01 | 2030-04-01 | 0 | 0 | 0 | Research Associate (DH) |  |  |  | blue2
1.4 | WP4: Prototyping real-world applications | group | 2024-04-01 | 2030-11-29 | 0 | 0 | 0
1.4.1 | Develop workshop on writing in a second language | task | 2024-12-03 | 2025-11-03 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.4.2 | Conduct 2+ workshops | task | 2025-12-03 | 2026-11-03 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.4.1 |  |  | purple1
1.4.3 | Make selected components of Bukvik and LitTerra available to researchers / public | task | 2028-02-01 | 2030-11-29 | 0 | 0 | 0 | Research Associate (DH) | 1.3.2 |  |  | blue2
1.4.4 | Develop and conduct workshops on influence and multilingualism | task | 2026-11-02 | 2027-07-01 | 0 | 0 | 0 | Eugenia Kelbert Rudan | 1.4.2 |  |  | blue2
1.4.5 | Apply to the New Generation Thinkers scheme | task | 2024-04-01 | 2024-09-05 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | blue2
1.5 | Other | group | 2024-01-01 | 2030-11-29 | 0 | 0 | 0
1.5.1 | Hiring process for team members | task | 2024-01-01 | 2024-04-10 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.5.2 | Training research stays in Utrecht and Frankfurt am MainÂ | task | 2024-02-01 | 2024-07-31 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.5.3 | Organise a new ICLA Research Committee on LCL | task | 2024-05-01 | 2030-11-29 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | purple1
1.5.4 | Liaise with the UEA Ethics teamÂ | task | 2024-02-01 | 2024-04-01 | 0 | 0 | 0 | Eugenia Kelbert Rudan |  |  |  | blue2